## Sheet3
Task | Start Date | Estimated Completion | Absolute Deadline | [36 empty] | Week beginning: | 2025-09-22 | 2025-09-29 | 2025-10-06 | 2025-10-13 | 2025-10-20 | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-17 | 2025-11-24 | 2025-12-01 | 2025-12-08 | 2025-12-15 | 2025-12-22 | 2025-12-29 | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18
REPORT: PID Submission | 2025-09-23 | 2025-09-26 | 2025-10-01 | [36 empty] | REPORT: PID Submission | bar: 2025-09-22 to 2025-09-29
REPORT: Ethics Form Application | 2025-10-22 |  | 2025-11-05 | [36 empty] | REPORT: Literature Review | bar: 2025-09-22 to 2025-10-27
REPORT: Satisfactory Progress Presentation | 2025-11-24 |  | 2025-12-08 | [36 empty] | DEVELOPMENT: Data Collection | bar: 2025-09-22 to 2025-10-06
REPORT: Final Submission | 2025-09-23 |  | 2026-05-06 | [36 empty] | DEVELOPMENT: Data Cleaning | bar: 2025-10-06
REPORT: Literature Review | 2025-09-23 | 2025-10-30 | [37 empty] | DEVELOPMENT: Data Preprocessing | bar: 2025-10-06 to 2025-10-13
DATA: Collecting Fresh Testing Data | 2025-11-06 | 2025-02-28 | [37 empty] | DEVELOPMENT: Prototype Model Development (small sample) | bar: 2025-10-13 to 2025-10-27
DATA: Refining Fresh Testing Data | 2025-11-06 | 2025-02-28 | [37 empty] | REPORT: Ethics Form Application | bar: 2025-10-20 to 2025-11-03
DEVELOPMENT: Data Collection | 2025-09-23 | [38 empty] | DEVELOPMENT: Scaling Prototype to Entire Dataset | bar: 2025-10-27 to 2025-11-10
DEVELOPMENT: Data Cleaning | [39 empty] | DEVELOPMENT: Testing Large Prototype | bar: 2025-11-03
DEVELOPMENT: Data Preprocessing | [39 empty] | DATA: Collecting Fresh Testing Data | bar: 2025-11-03 to 2026-03-02
DEVELOPMENT: Prototype Model Development (small sample) | [39 empty] | DATA: Refining Fresh Testing Data | bar: 2025-11-03 to 2026-03-02
DEVELOPMENT: Scaling Prototype to Entire Dataset | [39 empty] | DEVELOPMENT: First Official Iteration Development | bar: 2025-11-17 to 2025-12-08
DEVELOPMENT: Testing Large Prototype | [39 empty] | REPORT: Satisfactory Progress Presentation | bar: 2025-11-24 to 2025-12-08
DEVELOPMENT: First Official Iteration Development | [39 empty] | DEVELOPMENT: Second Official Iteration Development | bar: 2025-12-15 to 2026-01-05
DEVELOPMENT: Second Official Iteration Development | [39 empty] | DEVELOPMENT: Third Official Iteration Development | bar: 2026-01-12 to 2026-02-02
DEVELOPMENT: Third Official Iteration Development | [39 empty] | DEVELOPMENT: Fourth Official Iteration Development | bar: 2026-02-09 to 2026-03-02
DEVELOPMENT: Fourth Official Iteration Development | [39 empty] | DEVELOPMENT: Fifth Official Iteration Development | bar: 2026-03-09 to 2026-03-30
DEVELOPMENT: Fifth Official Iteration Development | [39 empty] | REPORT: Report Writing & Submission | bar: 2026-01-19 to 2026-05-04
Week Ending:
[5 empty] | 2025-09-26 | 2025-10-03 | 2025-10-10 | 2025-10-17 | 2025-10-24 | 2025-10-31 | 2025-11-07 | 2025-11-14 | 2025-11-21 | 2025-11-28 | 2025-12-05 | 2025-12-12 | 2025-12-19 | 2025-12-26 | 2026-01-02 | 2026-01-09 | 2026-01-16 | 2026-01-23 | 2026-01-30 | 2026-02-06 | 2026-02-13 | 2026-02-20 | 2026-02-27 | 2026-03-06 | 2026-03-13 | 2026-03-20 | 2026-03-27 | 2026-04-03 | 2026-04-10 | 2026-04-17 | 2026-04-24 | 2026-05-01 | 2026-05-08 | 2026-05-15 | 2026-05-22
REPORT: PID Submission | bar: 2025-09-26 to 2025-10-03
REPORT: Ethics Form Application | bar: 2025-10-24 to 2025-11-07
REPORT: Satisfactory Progress Presentation | bar: 2025-11-28 to 2025-12-12
REPORT: Report Writing & Submission | bar: 2026-01-23 to 2026-05-08
REPORT: Literature Review | bar: 2025-09-26 to 2025-10-31
DATA: Collecting Fresh Testing Data | bar: 2025-11-07 to 2026-03-06
DATA: Refining Fresh Testing Data | bar: 2025-11-07 to 2026-03-06
DEVELOPMENT: Data Collection | bar: 2025-09-26 to 2025-10-10
DEVELOPMENT: Data Cleaning | bar: 2025-10-10
DEVELOPMENT: Data Preprocessing | bar: 2025-10-10 to 2025-10-17
DEVELOPMENT: Prototype Model Development (small sample) | bar: 2025-10-17 to 2025-10-31
DEVELOPMENT: Scaling Prototype to Entire Dataset | bar: 2025-10-31 to 2025-11-14
DEVELOPMENT: Testing Large Prototype | bar: 2025-11-07 to 2025-11-14
DEVELOPMENT: First Official Iteration Development | bar: 2025-11-21 to 2025-12-12
DEVELOPMENT: Second Official Iteration Development | bar: 2025-12-19 to 2026-01-09
DEVELOPMENT: Third Official Iteration Development | bar: 2026-01-16 to 2026-02-06
DEVELOPMENT: Fourth Official Iteration Development | bar: 2026-02-13 to 2026-03-06
DEVELOPMENT: Fifth Official Iteration Development | bar: 2026-03-13 to 2026-04-03